## CR-05 - Goals and Outcomes

**Progress the jurisdiction has made in carrying out its strategic plan and its action plan. 91.520(a)**

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

During the period of October 1, 2020 through September 30, 2021, Jefferson County expended $2,254,843.58 in Community Development Block Grant (CDBG) funds to provide a suitable, living environment and safe, decent, affordable housing to low- to moderate-income residents of Jefferson County, Alabama.   During the period of October 1, 2020 through September 30, 2021,  Jefferson County completed zero (0) infrastructure/public facility activities and fifty-two (52) housing rehabilitation activities for fifty-two (52) households.  Additionally, sixteen (16) infrastructure/public facility activities, emergency housing rehabilitation activities, and six (6) public service activity were underway.

One (1)  HOME program award was made for the development of 52 newly constructed units of elderly rental housing.  The Villas at York will have 52 units comprised of one-  and two-bedroom units and is located in the unincorporated Grayson Valley area.  The Villas at York will utilize $896,056 in HOME Program funds and leverages Low Income Housing Tax Credits as well as private loan funds.  Construction was delayed due to the COVID-19 pandemic but is nearing completion for Cherry Woods Apartments which is also a 52 unit elderly rental development in the unincorporated Forestdale area of Jefferson County.  Total development costs for each development is approximately $10,000,000.

Two (2) single-family homes were rehabilitated and sold to income eligible homebuyers in the unincorporated Chalkville area of Jefferson County as a Community Housing Development Corporation (CHDO) project.  Another three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities.

**Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives. 91.520(g)**

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Goal** | **Category** | **Source / Amount** | **Indicator** | **Unit of Measure** | **Expected – Strategic Plan** | **Actual – Strategic Plan** | **Percent Complete** | **Expected – Program Year** | **Actual – Program Year** | **Percent Complete** |
| Acquisition | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 0 |   |   |   |   |
| CDBG General Administration | Administration | CDBG: $ | Other | Other | 10 | 12 |  120.00% | 12 | 12 |  100.00% |
| CHDO Administration | Affordable Housing | HOME: $ | Homeowner Housing Added | Household Housing Unit | 1 | 0 |  0.00% |   |   |   |
| CHDO Set-Aside | Affordable Housing | HOME: $ | Homeowner Housing Added | Household Housing Unit | 1 | 2 |  200.00% |   |   |   |
| Clearance and Remediation Activities | Non-Housing Community Development | CDBG: $ | Buildings Demolished | Buildings | 5 | 0 |  0.00% | 1 | 0 |  0.00% |
| Construction of Rental Units | Affordable Housing | CDBG: $ / HOME: $766550.25 | Rental units constructed | Household Housing Unit | 8 | 0 |  0.00% | 5 | 0 |  0.00% |
| Down Payment Assistance | Affordable Housing | HOME: $ | Direct Financial Assistance to Homebuyers | Households Assisted | 1 | 0 |  0.00% |   |   |   |
| Economic Development Assistance | Non-Housing Community Development | CDBG: $ | Jobs created/retained | Jobs | 5 | 0 |  0.00% | 1 | 0 |  0.00% |
| HESG Admin | Homeless | ESG: $ | Other | Other | 2 | 1 |  50.00% | 2 | 1 |  50.00% |
| HESG HMIS | Homeless | ESG: $ | Other | Other | 5 | 1 |  20.00% | 5 | 1 |  20.00% |
| HESG Homeless Prevention | Homeless | ESG: $ | Homelessness Prevention | Persons Assisted | 15 | 47 |  313.33% | 3 | 47 |  1,566.67% |
| HESG Rapid Re-Housing | Homeless | ESG: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 15 | 4 |  26.67% | 3 | 4 |  133.33% |
| HESG Shelter | Homeless | ESG: $ | Homeless Person Overnight Shelter | Persons Assisted | 500 | 1795 |  359.00% | 100 | 1795 |  1,795.00% |
| HESG Street Outreach | Homeless | ESG: $ | Other | Other | 25 | 1 |  4.00% | 5 | 1 |  20.00% |
| HOME Administration | Affordable Housing | HOME: $ | Other | Other | 4 | 4 |  100.00% | 2 | 4 |  200.00% |
| Homeownership | Affordable Housing | HOME: $ | Homeowner Housing Added | Household Housing Unit | 10 | 0 |  0.00% |   |   |   |
| Housing Program Delivery | Affordable Housing | CDBG: $ | Other | Other | 4 | 0 |  0.00% | 4 | 4 |  100.00% |
| Public Facilities | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 1000 | 22460 |  2,246.00% | 200 | 22460 |  11,230.00% |
| Public Facilities | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities for Low/Moderate Income Housing Benefit | Households Assisted | 500 | 0 |  0.00% | 100 | 0 |  0.00% |
| Public Services | HomelessNon-Homeless Special Needs | CDBG: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 50 |   | 0 | 50 |   |
| Public Services | HomelessNon-Homeless Special Needs | CDBG: $ | Public service activities for Low/Moderate Income Housing Benefit | Households Assisted | 500 | 0 |  0.00% | 100 | 2282 |  2,282.00% |
| Rehab of Homeowner Housing: Emergency Repairs | Affordable Housing | CDBG: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 100 | 0 |  0.00% | 20 | 52 |  260.00% |
| Rehabilitation of Rental Housing Units | Affordable Housing | HOME: $ | Rental units rehabilitated | Household Housing Unit | 3 | 3 |  100.00% |   |   |   |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

**Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.**

**Construction of Rental Units (HOME):** One (1)  HOME program award was made for the development of 52 newly constructed units of elderly rental housing.  The Villas at York will have 52 units comprised of one-  and two-bedroom units and is located in the unincorporated Grayson Valley area.  The Villas at York will utilize $896,056 in HOME Program funds and leverages Low Income Housing Tax Credits as well as private loan funds.  Construction was delayed due to the COVID-19 pandemic but is nearing completion for Cherry Woods Apartments which is also a 52 unit elderly rental development in the unincorporated Forestdale area of Jefferson County.  Total development costs for each development is approximately $10,000,000.

**CHDO Administration (HOME):**  There were no CHDO Administration activities planned for the program year.

**CHDO Set-Aside (HOME):**  Two (2) CHDO projects were completed during the program year.  Two (2) single-family homes were rehabilitated and sold to income eligible homebuyers in the unincorporated Chalkville area of Jefferson County as a Community Housing Development Corporation (CHDO) project.  Another three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities were reported under Rehabilitation of Rental Housing Units (HOME).

**Down Payment Assistance (HOME):**  There were no down payment assistance activities planned for the program year.

**HOME Administration (HOME):**  During the program year, four (4) employees conducted administrative functions under the HOME Program.

**Home Ownership (HOME):**  There were no home ownership activities planned for the 2020 program year.

**Rehabilitation of Rental Housing Units (HOME):**  There were no plans for the rehabilitation of rental housing units during the 2020 program. Three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities. year.

**Acquisition (CDBG):** No acquisition activities were planned during the program year.

**CDBG General Administration:** During the Program Year ten employees were involved with the administration of CDBG activities.

**Clearance and Remediation Activities (CDBG):** No clearance and remediation activities were funded from the program year.

**Economic Development Assistance (CDBG):** Jefferson County closed on multiple loans in the project year and expects to report on job creation and reteniton in the next CAPER.

**Housing Program Delivery (CDBG):** Four (4) employees provided housing program delivery services related to CDBG housing activities during the program year.

 **Public Facilities (CDBG):**   During the program year zero (0) public facility activities have been completed and another sixteen (16) are in design or under construction.

## CR-10 - Racial and Ethnic composition of families assisted

**Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **CDBG** | **HOME** | **ESG** |
| White | 507 | 0 | 643 |
| Black or African American | 1,841 | 5 | 1,132 |
| Asian | 1 | 0 | 4 |
| American Indian or American Native | 0 | 0 | 8 |
| Native Hawaiian or Other Pacific Islander | 0 | 0 | 1 |

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
| **Total** | **2,349** | **5** | **1,788** |

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
| Hispanic | 16 | 0 | 73 |
| Not Hispanic | 2,333 | 5 | 1,772 |

**Table 2 – Table of assistance to racial and ethnic populations by source of funds**

**Narrative**

HOME: A total of five (5) families were assisted through the single-family homebuyer and rental houses developed by the CHDO.

## CR-15 - Resources and Investments 91.520(a)

**Identify the resources made available**

|  |  |  |  |
| --- | --- | --- | --- |
| **Source of Funds** | **Source** | **Resources Made Available** | **Amount Expended During Program Year** |
| CDBG | public - federal | 2,414,125 | 2,254,844 |
| HOME | public - federal | 1,021,826 | 232,090 |
| ESG | public - federal | 204,775 | 159,664 |

Table 3 - Resources Made Available

**Narrative**

During the period of October 1, 2020 through September 30, 2021, Jefferson County received $2,414,125.00 in CDBG funds; $12,128.88 in CDBG program income; $1,021,826.00 in HOME funds; 0.00 in HOME matching funds; $0.00 in County Match; and $204,775.00 in Federal ESG making a total of $3,652,854.88 in funds available for Program Year 2020.

Additionally, Jefferson County expended $1,896,366.45 of the $5,455,632.00 in CDBG-CV and ESG-CV funding.

**Identify the geographic distribution and location of investments**

|  |  |  |  |
| --- | --- | --- | --- |
| **Target Area** | **Planned Percentage of Allocation** | **Actual Percentage of Allocation** | **Narrative Description** |
|  |  |  |  |

Table 4 – Identify the geographic distribution and location of investments

**Narrative**

During the period of October 1, 2020 through September 30, 2021 CDBG funds were drawn for activities within the following geographical locations: County-wide including unincorporated areas of Jefferson County for Housing Rehabilitation and Public Service activities; Public Facilities in the municipalities of Irondale, Center Point, Brighton, Lipscomb, Mulga, Graysville, Pinson, Midfield, Fairfield, and Leeds, plus public facilities in unincorporated areas of Jefferson County including Edgewater.

 Completed HOME funded CHDO single-family homebuyer and rental units are located in the City of Clay, Hueytown and in the unincorporated Edgewater and Chalkville areas of Jefferson County.  A HOME funded elderly rental development in the unincorporated Forestdale area is under construction.  Another elderly rental development in the unincorporated Grayson Valley area of Jefferson County has been awarded County HOME funds as well as Low-Income Housing Tax Credits from the Alabama Housing Finance Authority during the reporting period with construction beginning during the following Program Year.

**Leveraging**

**Explain how federal funds leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.**

The HOME Program did not leverage any private loans, grants, and Low Income Housing Tax Credits during the reporting period of October 1, 2020 – September 30, 2021.  Construction on the Cherry Woods Apartments was delayed due to the COVID-19 pandemic and was not completed during the reporting period.  Funds leveraged for this project will be reported in the following Program Year.

Jefferson County received a 100% HOME match waiver for the reporting period due to COVID-19.  No publicly owned land was used to address the needs identified in the plan for the HOME Program.

| **Fiscal Year Summary – HOME Match** |
| --- |
| 1. Excess match from prior Federal fiscal year | 2,071,751 |
| 2. Match contributed during current Federal fiscal year | 0 |
| 3. Total match available for current Federal fiscal year (Line 1 plus Line 2) | 2,071,751 |
| 4. Match liability for current Federal fiscal year | 0 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | 2,071,751 |

Table 5 – Fiscal Year Summary - HOME Match Report

|  **Match Contribution for the Federal Fiscal Year** |
| --- |
| **Project No. or Other ID** | **Date of Contribution** | **Cash****(non-Federal sources)** | **Foregone Taxes, Fees, Charges** | **Appraised Land/Real Property** | **Required Infrastructure** | **Site Preparation, Construction Materials, Donated labor** | **Bond Financing** | **Total Match** |
|  |  |  |  |  |  |  |  |  |

Table 6 – Match Contribution for the Federal Fiscal Year

**HOME MBE/WBE report**

| **Program Income** – Enter the program amounts for the reporting period |
| --- |
| **Balance on hand at begin-ning of reporting period****$** | **Amount received during reporting period****$** | **Total amount expended during reporting period****$** | **Amount expended for TBRA****$** | **Balance on hand at end of reporting period****$** |
| 0 | 0 | 0 | 0 | 0 |

Table 7 – Program Income

|  |
| --- |
| **Minority Business Enterprises and Women Business Enterprises –** Indicate the number and dollar value of contracts for HOME projects completed during the reporting period |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Total** | **Minority Business Enterprises** | **White Non-Hispanic** |
| **Alaskan Native or American Indian** | **Asian or Pacific Islander** | **Black Non-Hispanic** | **Hispanic** |

|  |
| --- |
| **Contracts** |
|  |  |  |  |  |  |  |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |

|  |
| --- |
| **Sub-Contracts** |
|  |  |  |  |  |  |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Total** | **Women Business Enterprises** | **Male** |

|  |
| --- |
| **Contracts** |
|  |  |  |  |
| Dollar Amount | 0 | 0 | 0 |
| Number | 0 | 0 | 0 |

|  |
| --- |
| **Sub-Contracts** |
|  |  |  |  |
| Number | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 |

Table 8 - Minority Business and Women Business Enterprises

|  |
| --- |
| **Minority Owners of Rental Property** – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Total** | **Minority Property Owners** | **White Non-Hispanic** |
| **Alaskan Native or American Indian** | **Asian or Pacific Islander** | **Black Non-Hispanic** | **Hispanic** |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

Table 9 – Minority Owners of Rental Property

|  |
| --- |
| **Relocation and Real Property Acquisition –** Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition |

|  |  |  |
| --- | --- | --- |
|  | **Number** | **Cost** |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Households Displaced** | **Total** | **Minority Property Enterprises** | **White Non-Hispanic** |
| **Alaskan Native or American Indian** | **Asian or Pacific Islander** | **Black Non-Hispanic** | **Hispanic** |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | 0 | 0 | 0 | 0 | 0 | 0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

**Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.**

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Non-Homeless households to be provided affordable housing units | 0 | 5 |
| Number of Special-Needs households to be provided affordable housing units | 5 | 0 |
| **Total** | **5** | **5** |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 0 | 0 |
| Number of households supported through The Production of New Units | 5 | 0 |
| Number of households supported through Rehab of Existing Units | 0 | 5 |
| Number of households supported through Acquisition of Existing Units | 0 | 0 |
| **Total** | **5** | **5** |

Table 12 – Number of Households Supported

**Discuss the difference between goals and outcomes and problems encountered in meeting these goals.**

HOME:  Construction on the Cherry Woods Apartments was delayed due to the COVID-19 pandemic and was not completed during the reporting period.  Outcomes for this project will be reported in the following Program Year.

Two (2) CHDO projects were completed during the program year.  Two (2) single-family homes were rehabilitated and sold to income eligible homebuyers in the unincorporated Chalkville area of Jefferson County as a Community Housing Development Corporation (CHDO) project.  Another three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities were reported under Rehabilitation of Rental Housing Units (HOME).

**Discuss how these outcomes will impact future annual action plans.**

Given the small number of proposals received coupled with the impact of the new HOME rules, future action plans will define activities as broadly as possible to enhance our ability to attract as many financially sound proposals from developers with a strong track record as possible.  Site availability continues to be an issue so no target areas will be identified to help increase the number of viable proposals.  The rehabilitation of existing units will also alieviate the limited choice of building sites.

**Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.**

|  |  |  |
| --- | --- | --- |
| **Number of Households Served** | **CDBG Actual** | **HOME Actual** |
| Extremely Low-income | 34 | 1 |
| Low-income | 12 | 1 |
| Moderate-income | 6 | 3 |
| **Total** | **52** | **5** |

Table 13 – Number of Households Served

**Narrative Information**

Under the HOME Program, a total of five (5) families were assisted through the single-family homebuyer and rental houses developed by the CHDO.

Under the CDBG program, there were 34 beneficiaries below 30% median area income.

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

**Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:**

**Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs**

Jefferson County has partnered with One Roof to provide Street Outreach services to homeless persons for the assessment of their individual needs.  During the program year, Jefferson County made $20,417.00 in HESG Street Outreach funds available specifically for reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs.

**Addressing the emergency shelter and transitional housing needs of homeless persons**

Jefferson County has maintained an interactive approach in the coordination of services with the local Continuum of Care (CoC) in order to address emergency shelter and transitional housing needs of homeless individuals and families.  The needs, availability and gaps are submitted to Jefferson County by One Roof upon request.

During the 2020 program year Jefferson County continued support of agencies that provided transitional supportive housing and permanent housing to homeless individuals; shelter to homeless families with minor children; day shelters and transitional housing programs for women and children; shelter for victims of domestic violence; transitional housing for single women; daycare for homeless children; after-school activities for homeless children of school age; and services to homeless families.

**Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are: likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions); and, receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs**

Jefferson County assisted low-income, especially extremely low-income individuals and families avoid becoming homeless by providing homeless prevention services to qualified applicants.  Under the fourth program year of the Consolidated Plan, Jefferson County has continued to work closely with the CoC in the coordination of prevention programs in implementing discharge coordination policies for foster care, healthcare, mental health, and the correction system.

**Child Welfare**: The State of Alabama Department of Human Resources developed policy mandates that all youth in care of the State of Alabama through the Department of Human Resources (foster care) are evaluated by their case managers at high school graduation or upon aging out of the system, whichever comes first, for placement in transitional housing programs managed by Gateway, a non-McKinney Vento funded program.

**Physical Health Institutions**: In spite of years of work on a coordinated system of discharge from health care, there is no policy in place.

**Mental Health Institutions**: State policy prohibits discharge (DC) of clients into homelessness: Alabama Department of Mental Health (DMH) policy for state facilities is that DC planning is done by case workers with consumer involvement and input.  Patients are DC’d to family, certified group homes or permitted boarding homes ONLY.

**Juvenile and Adult Corrections**: CoC member, AIDS Alabama, works with receptive local, state and federal correctional facilities to provide discharge services.

**Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again**

Jefferson County has helped homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness; facilitating access for homeless individuals and families to affordable housing units; and preventing individuals and families who were recently homeless from becoming homeless again by making Homelessness Prevention and Rapid Re-Housing funds available to local service providers.  Local service providers must submit annual applications for Emergency Solutions Grant (ESG) funding to Jefferson County for upcoming program year funds.  Funds are awarded on a competitive basis within the categories allocated within that year’s One-Year Annual Action Plan.

## CR-30 - Public Housing 91.220(h); 91.320(j)

**Actions taken to address the needs of public housing**

Jefferson County continues to support the efforts of Consortuim Public Housing Authorities (PHA’s) to address the needs of public housing and public housing activities through the execution of Letters of Consistency supporting their funding initatives.  Jefferson County further supported the efforts of Consortuim PHA’s to encourage public housing residents to become more involved in management and encourage their interest and efforts to move to homeowership through the same mechanism and by working with them with its HOME homeownership assistance program.  Jefferson County also enlists the help and support of the Consortium PHA’s during the Open Season period.

**Actions taken to encourage public housing residents to become more involved in management and participate in homeownership**

The Jefferson County Housing Authority (JCHA) continues to collaborate with local banks and mortgage lenders in an effort to provide homeownership and credit information to its public housing residents.  JCHA periodically holds homebuyer workshops, financial literacy seminars, and self-empowerment seminars.  Primary homeownership focus is given to available mortgage products, lending practices, fair housing practices, how to secure a mortgage through credit worthiness, the importance of obtaining a home inspection, insurance, and the importance of obtaining a realtor.

**Actions taken to provide assistance to troubled PHAs**

There are currently no troubled PHAs in Jefferson County, Alabama for which assistance is needed.  Should any become troubled, however, Jefferson County will continue to work with them in addressing the PHA needs and providing residents with opportunities.

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

**Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)**

Jefferson County did not take any actions to remove or ameliorate land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment because those potential barriers did not affect housing activities during the Program Year.

**Actions taken to address obstacles to meeting underserved needs. 91.220(k); 91.320(j)**

During the 2020 Program Year (October 1, 2020 – September 30, 2021) Jefferson County issued a Request for Proposals for Rental Housing which was for the 2020 and 2021 Low Income Housing Tax Credit application cycle for the Alabama Housing Finance Authority (AHFA).  A preliminary award letter for permanent financing under the HOME Program in the amount of $832,052.00 was given to a fifty-two (52) unit elderly development in the unincorporated Grayson Valley area.  The project was awarded Low Income Housing Tax Credits from the Alabama Housing Finance Authority during their 2021 application cycle.

**Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)**

All HOME and CDBG Program agreements prohibit the use of lead-based paint.  Additionally, units assisted with HESG funds must comply with ESG Lead-based paint policies, standards, visual lead-based paint inspections, and remediation or alternative actions to reduce lead-based paint hazards.

 The CDBG Housing Rehabilitation program utilizes a State licensed and accredited third-party firm to perform all out lead-based paint testing.  The Housing Division has tests performed on all areas where rehabilitation work will possibly disturb lead-based paint in pre 1978 target housing.

**Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)**

Construction is nearing completion for the development of  52 new units of elderly rental housing.  Cherry Woods Apartments located in the unincorporated Forestdale area of Jefferson County has 52 one- and two-bedroom units and leverages Low Income Housing Tax Credits and private loan funds.

Two (2) CHDO projects were completed during the program year.  Two (2) single-family homes were rehabilitated and sold to income eligible homebuyers in the unincorporated Chalkville area of Jefferson County as a Community Housing Development Corporation (CHDO) project.  Another three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities.

Another elderly rental development, The Villas at York, has been awarded Low Income Housing Tax Credits by the Alabama Housing Finance Authority and will also leverage private loan funds.  The development consists of fifty-two (52) one-and two-bedroom units and is located in the unincorporated Chalkville area.  Jefferson County will contribute $896,056, in HOME Program funds.  Construction will begin in the following Program Year.

**Non-Housing:**

Jefferson County through the Birmingham Career Center has four (4) main goals to assist in the anti-poverty strategy: 1) Create a delivery system that meets the needs of both employers and job seekers for a range of services, including customized services; 2) Create an effective and cost efficient transitional support system to promote job retention; 3) Create an integrated, results oriented career center system that provides easy access for both job seekers and employers to an array of quality services that promote workforce development; and 4) Maintain a system that will empower individuals with the knowledge to choose the services they require, and develop a system that will make local service providers accountable for meeting those needs.  Jefferson County’s eligible ESG Homeless Prevention applicants may also receive referrals to the Career Center in efforts to help them gain and remain self-sustainable.

For non-housing construction projects contractors are encouraged to adhere to the County’s Section 3 Plan in the notification, hiring and reporting of section three (3) residents to fill vacant positions needed for the development of the section 3 covered activity.

**Actions taken to develop institutional structure. 91.220(k); 91.320(j)**

Jefferson County’s HOME Program has successfully solicited outside sources of funds through both public and private sectors including Low Income Housing Tax Credits, private loans and private grants.

 The Community Development Block Grant and Emergency Solutions Grant programs have continued to work with the local CoC and a variety of local non-profit entities to support initiatives to benefit the homeless, those at-risk of homelessness, and low- to moderate-income individuals and families of Jefferson County.

**Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)**

Jefferson County’s HOME Program has successfully solicited outside sources of funds for multiple developments including Cherry Woods Apartments and The Villas at York through both public and private sectors including Low Income Housing Tax Credits, private loans and private grants.  Hickory Ridge 3 was developed and is owned by JCHA Housing and Development Corporation which is the non-profit development arm of the Jefferson County Housing Authority. Abbington at Summit Pointe and Hickory Ridge 3 have been completed and are fully leased.  Construction on Chery Woods Apartments is nearing completion.  The Villas at York will begin construction in the following Program Year.

Jefferson County successfully worked with a Community Housing Development Organization (CHDO) to complete two (2) HOME CHDO projects during the program year.  Two (2) single-family homes were rehabilitated and sold to income eligible homebuyers in the unincorporated Chalkville area of Jefferson County as a Community Housing Development Corporation (CHDO) project.  Another three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities.

The case managers of Jefferson County’s ESG Program may make recommendations to public and private housing and social service agencies to provide services to those who are homeless and those at-risk of homelessness in efforts to reach self-sustainability for those individuals and families.

**Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice. 91.520(a)**

During the reporting period of October 1, 2020 to September 30, 2021 Jefferson County undertook the following actions to overcome the effects of impediments identified the analysis of impediments to fair housing choice:

1. Addressed the Cost Burden of lower income households by using CDBG funds for 52 homeowner rehabilitation cases.

2. Placed Fair Housing posters and educational materials at public events to help increase public awareness of the housing options available to lower income households and what the individual’s rights are under the law.  Jefferson County further incorporated the Fair Housing logo in all our housing promotional materials.

3. Committed HOME Program funds for the development of fifty-two (52) units of Special Needs Rental Housing for the Elderly to increase the supply of affordable housing.  Construction is nearing completion.

4. Jefferson County further issued a Request for Proposals for Rental Housing.  A preliminary award letter for permanent financing under the HOME Program in the amount of $896,056.00 was given to a fifty-two (52) unit elderly development in the unincorporated Grayson Valley area.  The project was awarded Low Income Housing Tax Credits from the Alabama Housing Finance Authority during their 2021 application cycle.  Construction should begin in the following Program Year.

5. Jefferson County successfully worked with a Community Housing Development Organization (CHDO) to complete two (2) HOME CHDO projects during the program year.  Two (2) single-family homes were rehabilitated and sold to income eligible homebuyers in the unincorporated Chalkville area of Jefferson County as a Community Housing Development Corporation (CHDO) project.  Another three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities.

6. The lack of Section “8” Vouchers and Certificates which limits the housing options to lower income households was addressed by underwriting the new rental housing units at rents below the HOME Maximum Rent Limits for the Birmingham-Hoover MSA thereby increasing the number of affordable units available to lower income households.

7. The lack of accessible housing was addressed by incorporating fully accessible and sensory impaired units into the construction of new rental housing funded under the HOME Program.  CDBG funds were used to assist 52 elderly/disabled homeowners.

## CR-40 - Monitoring 91.220 and 91.230

**Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements**

Jefferson County continues to implement its standards and procedures to monitor activities carried out in furtherance of the plan.  Those procedures that involve long-term compliance with the requirements of the Consolidated Plan and Annual Action Plans have included obligatory contractual language, regular on-site monitoring, and may also include desk monitoring which included, but was not limited to fair housing, civil rights, and minority business outreach.

**Citizen Participation Plan 91.105(d); 91.115(d)**

**Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports**.

The Jefferson County Office of Community Services and Workforce Development advertised the CAPER for the Program Year in *The Birmingham Times* on Thursday, November 25, 2021;  in *The Birmingham News* on Friday, November 26, 2021; and and *The Latino-News* on Friday, November 26, 2021.

A public hearing was scheduled for 10:00 a.m. on Friday, December  3, 2021 in room A-420 of the Jefferson County Courthouse in Downtown Birmingham (716 Richard Arrington Jr Blvd N, Birmingham, AL 35203).  Copies of the CAPER were made available at thirty-four (34) different municipalities located throughout Jefferson County.  Additionally, a copy of the CAPER was made available on the County’s website at www.jccal.org.

 The deadline for submitting written comments regarding the CAPER  to the Jefferson County Office of Community Services & Workforce Development, 716 Richard Arrington Jr Blvd N, Suite A-430, Birmingham, AL 35203, Attn: CAPER Comments was 5:00 p.m. on December 10, 2021.

**CR-45 - CDBG 91.520(c)**

**Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.**

Jefferson County has not made any changes to program objectives and does not recommend any changes to the program at this time.

**Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?**

No

**[BEDI grantees] Describe accomplishments and program outcomes during the last year.**

## CR-50 - HOME 91.520(d)

**Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations**

Please list those projects that should have been inspected on-site this program year based upon the schedule in §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

Jefferson County was issued an inspection waiver by HUD due to COVID-19 during the reporting period.  Inspections will resume at a later date when the pandemic has subsided.

**Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 92.351(b)**

A list of all rental developments with contact information was provided at three (3) public hearings and two (2) Technical Advisory Committee meetings.  The meetings were advertised in *The Birmingham News*, *The Birmingham Times*, *The Latino News, and* was also announced by mail to local mayors, public housing agencies, and community leaders.

**Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics**

Not applicable.

**Describe other actions taken to foster and maintain affordable housing. 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 91.320(j)**

Construction is nearing completion for the development of  52 new units of elderly rental housing.  Cherry Woods Apartments located in the unincorporated Forestdale area of Jefferson County has 52 one- and two-bedroom units and leverages Low Income Housing Tax Credits and private loan funds.

Two (2) CHDO projects were completed during the program year.  Two (2) single-family homes were rehabilitated and sold to income eligible homebuyers in the unincorporated Chalkville area of Jefferson County as a Community Housing Development Corporation (CHDO) project.  Another three (3) single-family homes were rehabilitated and rented to income eligible tenants by a qualified CHDO in the Clay, Edgewater and Hueytown communities.

Another elderly rental development, The Villas at York, has been awarded Low Income Housing Tax Credits by the Alabama Housing Finance Authority and will also leverage private loan funds.  The development consists of fifty-two (52) one-and two-bedroom units and is located in the unincorporated Chalkville area.  Jefferson County will contribute $896,056, in HOME Program funds.  Construction will begin in the following Program Year.

## CR-60 - ESG 91.520(g) (ESG Recipients only)

**ESG Supplement to the CAPER in *e-snaps***

**For Paperwork Reduction Act**

**1. Recipient Information—All Recipients Complete**

**Basic Grant Information**

|  |  |
| --- | --- |
| **Recipient Name** | JEFFERSON COUNTY |

|  |  |
| --- | --- |
| **Organizational DUNS Number** | 105474279 |

|  |  |
| --- | --- |
| **EIN/TIN Number** | 636001579 |

|  |  |
| --- | --- |
| **Indentify the Field Office** | BIRMINGHAM |

|  |  |
| --- | --- |
| **Identify CoC(s) in which the recipient or subrecipient(s) will provide ESG assistance** | Birmingham/Jefferson, St. Clair, Shelby Counties CoC |

**ESG Contact Name**

|  |  |
| --- | --- |
| **Prefix** | Dr |

|  |  |
| --- | --- |
| **First Name** | Frederick |

|  |  |
| --- | --- |
| **Middle Name** | L |

|  |  |
| --- | --- |
| **Last Name** | Hamilton |

|  |  |
| --- | --- |
| **Suffix** | 0 |

|  |  |
| --- | --- |
| **Title** | Director |

**ESG Contact Address**

|  |  |
| --- | --- |
| **Street Address 1** | 716 Richard Arrington Jr Blvd N |

|  |  |
| --- | --- |
| **Street Address 2** | Suite A430 |

|  |  |
| --- | --- |
| **City** | Birmingham |

|  |  |
| --- | --- |
| **State** | AL |

|  |  |
| --- | --- |
| **ZIP Code** | 35203- |

|  |  |
| --- | --- |
| **Phone Number** | 2053255761 |

|  |  |
| --- | --- |
| **Extension** | 0 |

|  |  |
| --- | --- |
| **Fax Number** | 0 |

|  |  |
| --- | --- |
| **Email Address** | hamiltonf@jccal.org |

**ESG Secondary Contact**

|  |  |
| --- | --- |
| **Prefix** | Mr |

|  |  |
| --- | --- |
| **First Name** | Nathan |

|  |  |
| --- | --- |
| **Last Name** | Salter |

|  |  |
| --- | --- |
| **Suffix** | 0 |

|  |  |
| --- | --- |
| **Title** | Grants Administrator |

|  |  |
| --- | --- |
| **Phone Number** | 2055217569 |

|  |  |
| --- | --- |
| **Extension** | 0 |

|  |  |
| --- | --- |
| **Email Address** | saltern@jccal.org |

**2. Reporting Period—All Recipients Complete**

|  |  |
| --- | --- |
| **Program Year Start Date** | 10/01/2020 |

|  |  |
| --- | --- |
| **Program Year End Date** | 09/30/2021 |

**3a. Subrecipient Form – Complete one form for each subrecipient**

|  |
| --- |
| **Subrecipient or Contractor Name:** JEFFERSON COUNTY**City:** Birmingham**State:** AL**Zip Code:** 35203, 0100**DUNS Number:** 105474279**Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Unit of Government**ESG Subgrant or Contract Award Amount:** 15358 |
| **Subrecipient or Contractor Name:** Cooperative Downtown Ministries**City:** Birmingham**State:** AL**Zip Code:** 35203, 1828**DUNS Number:** 827210816**Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 25000 |
| **Subrecipient or Contractor Name:** PATHWAYS**City:** Birmingham**State:** AL**Zip Code:** 35203, 3308**DUNS Number:** 827210907**Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 25000 |
| **Subrecipient or Contractor Name:** BRIDGE MINISTRIES, INC.**City:** Birmingham**State:** AL**Zip Code:** 35205, 4804**DUNS Number:** 940075807**Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 40000 |
| **Subrecipient or Contractor Name:** YWCA (Interfaith Hospitality House)**City:** Birmingham**State:** AL**Zip Code:** 35203, 3820**DUNS Number:** 018394049**Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 19000 |
| **Subrecipient or Contractor Name:** YWCA (Family Violence Center)**City:** Birmingham**State:** AL**Zip Code:** 35203, 3820**DUNS Number:** 018394049**Is subrecipient a victim services provider:** Y**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 10000 |
| **Subrecipient or Contractor Name:** Dannon Project - Rapid Re-housing**City:** Birmingham**State:** AL**Zip Code:** 35203, 3408**DUNS Number:** **Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 25000 |
| **Subrecipient or Contractor Name:** One Roof**City:** Birmingham**State:** AL**Zip Code:** 35233, **DUNS Number:** **Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 20417 |
| **Subrecipient or Contractor Name:** Youth Towers**City:** Birmingham**State:** AL**Zip Code:** 35214, **DUNS Number:** **Is subrecipient a victim services provider:** N**Subrecipient Organization Type:** Other Non-Profit Organization**ESG Subgrant or Contract Award Amount:** 25000 |

## CR-65 - Persons Assisted

**4. Persons Served**

**4a. Complete for Homelessness Prevention Activities**

|  |  |
| --- | --- |
| **Number of Persons in Households** | **Total** |
| Adults | 19 |
| Children | 28 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| **Total** | **47** |

Table 16 – Household Information for Homeless Prevention Activities

**4b. Complete for Rapid Re-Housing Activities**

|  |  |
| --- | --- |
| **Number of Persons in Households** | **Total** |
| Adults | 4 |
| Children | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| **Total** | **4** |

Table 17 – Household Information for Rapid Re-Housing Activities

**4c. Complete for Shelter**

|  |  |
| --- | --- |
| **Number of Persons in Households** | **Total** |
| Adults | 1,590 |
| Children | 203 |
| Don't Know/Refused/Other | 2 |
| Missing Information | 0 |
| **Total** | **1,795** |

Table 18 – Shelter Information

**4d. Street Outreach**

|  |  |
| --- | --- |
| **Number of Persons in Households** | **Total** |
| Adults | 1 |
| Children | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| **Total** | **1** |

Table 19 – Household Information for Street Outreach

**4e. Totals for all Persons Served with ESG**

|  |  |
| --- | --- |
| **Number of Persons in Households** | **Total** |
| Adults | 1,614 |
| Children | 231 |
| Don't Know/Refused/Other | 2 |
| Missing Information | 0 |
| **Total** | **1,847** |

Table 20 – Household Information for Persons Served with ESG

**5. Gender—Complete for All Activities**

|  |  |
| --- | --- |
|  | **Total** |
| Male | 806 |
| Female | 528 |
| Transgender | 13 |
| Don't Know/Refused/Other | 24 |
| Missing Information | 476 |
| **Total** | **1,847** |

Table 21 – Gender Information

**6. Age—Complete for All Activities**

|  |  |
| --- | --- |
|  | **Total** |
| Under 18 | 231 |
| 18-24 | 123 |
| 25 and over | 1,491 |
| Don't Know/Refused/Other | 2 |
| Missing Information | 0 |
| **Total** | **1,847** |

Table 22 – Age Information

**7. Special Populations Served—Complete for All Activities**

**Number of Persons in Households**

| **Subpopulation** | **Total** | **Total Persons Served – Prevention** | **Total Persons Served – RRH** | **Total Persons Served in Emergency Shelters** |
| --- | --- | --- | --- | --- |
| Veterans | 90 | 1 | 1 | 88 |
| Victims of Domestic Violence | 292 | 2 | 1 | 289 |
| Elderly | 141 | 1 | 3 | 137 |
| HIV/AIDS | 40 | 0 | 0 | 40 |
| Chronically Homeless | 395 | 0 | 3 | 391 |

| **Persons with Disabilities:** |
| --- |
| Severely Mentally Ill | 602 | 0 | 2 | 600 |
| Chronic Substance Abuse | 492 | 0 | 0 | 492 |
| Other Disability | 441 | 4 | 3 | 434 |
| Total (Unduplicated if possible) | 0 | 0 | 0 | 0 |

Table 23 – Special Population Served

## CR-70 – ESG 91.520(g) - Assistance Provided and Outcomes

**10. Shelter Utilization**

|  |  |
| --- | --- |
| Number of New Units - Rehabbed | 0 |
| Number of New Units - Conversion | 0 |
| Total Number of bed-nights available | 0 |
| Total Number of bed-nights provided | 0 |
| Capacity Utilization | 0.00% |

Table 24 – Shelter Capacity

**11. Project Outcomes Data measured under the performance standards developed in consultation with the CoC(s)**

During the 2020 Program Year Jefferson County expended Emergency Solutions Grant (ESG) funds for Shelters, HMIS, Homelessness Prevention and Administrative activities.  The CoC continues to have difficulty in capturing the total number of bed-nights provided as that documentation is no longer tracked in HMIS.  The CoC continues the process of working with HUD and the software developer to determine a process for capturing that data.

Over the program year Jefferson County continued  consultations with the local CoC (AL-500-Birmingham/Jefferson, St. Clair, Shelby Counties CoC) regarding performance standards for the CoC which consists of over 30 organizations.

Additionally, Jefferson County has contracted with One Roof to administer and measure performance of the ESG-CV program.

## CR-75 – Expenditures

**11. Expenditures**

**11a. ESG Expenditures for Homelessness Prevention**

|  |  |
| --- | --- |
|  | **Dollar Amount of Expenditures in Program Year** |
|  | **2018** | **2019** | **2020** |
| Expenditures for Rental Assistance | 26,984 | 27,853 | 0 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 0 | 0 | 0 |
| Expenditures for Homeless Prevention under Emergency Shelter Grants Program | 0 | 0 | 0 |
| **Subtotal Homelessness Prevention** | **26,984** | **27,853** | **0** |

Table 25 – ESG Expenditures for Homelessness Prevention

**11b. ESG Expenditures for Rapid Re-Housing**

|  |  |
| --- | --- |
|  | **Dollar Amount of Expenditures in Program Year** |
|  | **2018** | **2019** | **2020** |
| Expenditures for Rental Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 0 | 0 | 0 |
| Expenditures for Homeless Assistance under Emergency Shelter Grants Program | 0 | 0 | 0 |
| **Subtotal Rapid Re-Housing** | **0** | **0** | **0** |

Table 26 – ESG Expenditures for Rapid Re-Housing

**11c. ESG Expenditures for Emergency Shelter**

|  |  |
| --- | --- |
|  | **Dollar Amount of Expenditures in Program Year** |
|  | **2018** | **2019** | **2020** |
| Essential Services | 0 | 0 | 0 |
| Operations | 0 | 82,985 | 0 |
| Renovation | 0 | 0 | 0 |
| Major Rehab | 0 | 0 | 0 |
| Conversion | 0 | 0 | 0 |
| **Subtotal** | **0** | **82,985** | **0** |

Table 27 – ESG Expenditures for Emergency Shelter

**11d. Other Grant Expenditures**

|  |  |
| --- | --- |
|  | **Dollar Amount of Expenditures in Program Year** |
|  | **2018** | **2019** | **2020** |
| Street Outreach | 0 | 5,000 | 0 |
| HMIS | 0 | 9,450 | 0 |
| Administration | 0 | 14,391 | 0 |

Table 28 - Other Grant Expenditures

**11e. Total ESG Grant Funds**

|  |  |  |  |
| --- | --- | --- | --- |
| **Total ESG Funds Expended** | **2018** | **2019** | **2020** |
| 166,663 | 26,984 | 139,679 | 0 |

Table 29 - Total ESG Funds Expended

**11f. Match Source**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **2018** | **2019** | **2020** |
| Other Non-ESG HUD Funds | 26,984 | 139,679 | 0 |
| Other Federal Funds | 0 | 0 | 0 |
| State Government | 0 | 0 | 0 |
| Local Government | 0 | 0 | 0 |
| Private Funds | 0 | 0 | 0 |
| Other | 0 | 0 | 0 |
| Fees | 0 | 0 | 0 |
| Program Income | 0 | 0 | 0 |
| **Total Match Amount** | **26,984** | **139,679** | **0** |

Table 30 - Other Funds Expended on Eligible ESG Activities

**11g. Total**

|  |  |  |  |
| --- | --- | --- | --- |
| **Total Amount of Funds Expended on ESG Activities** | **2018** | **2019** | **2020** |
| 333,326 | 53,968 | 279,358 | 0 |

Table 31 - Total Amount of Funds Expended on ESG Activities